LFA Terms of Reference: Verification of Health Products Expiries

June 2026

Introduction

Effective supply chain management is critical to ensure uninterrupted availability of quality-assured health products for HIV, tuberculosis (TB) and malaria programs. Global supply chain disruptions, programmatic changes, treatment guideline updates, regimen transitions, forecasting challenges, and distribution inefficiencies may contribute to mismatches between supply and demand, resulting in stock imbalances and risk of product expiry.

To safeguard program effectiveness, supply chain integrity and ensure efficient use of resources, it is important to regularly assess stock levels, expired commodities, and products at risk of expiry across supply chain levels. This exercise supports improved stock management practices and informs corrective and preventive actions.

This TOR provides guidance for Global Fund Country Teams (CTs) and Local Fund Agents (LFAs) to adapt, based on country context, the process for LFA verification of health products that have expired and those that are at risk of expiring.

- Objectives

The objective of this verification is to:

- Assess quantities and value (if requested by the Global Fund CT) of health products that expired within the past 12 months;

- Identify health products at risk of expiry within the next 6 months;

- Verify alignment between stock levels, consumption patterns, and expiry risk;

- Identify root causes of expiries and stock imbalances; and

- Provide actionable recommendations to mitigate future risks.

- Scope of review

The review should cover tracer products for HIV, TB and malaria programs irrespective of the funding source for procurement of those commodities in the country. The selection of tracer products should be based on the treatment regimens and the mix of HIV, TB and malaria products used in the country. Where possible the analysis should separate the quantity of products by funding source (Global Fund vs. others). Where this differentiation by funding source is not possible, the LFA should clearly indicate this limitation.

The scope of the review should cover at minimum the central medical stores (CMS) or national warehouses and, based on inventory distribution, stock positioning in the country and feasibility, expand to selected regional or provincial warehouses and selected high-volume facilities, as relevant and required by the Global Fund CT. The Global Fund CT may also decide to execute the CMS level assessment first and based on the preliminary results, expand the scope to relevant downstream storage locations.

The scope of the verification can be expanded to include inventory management policies and practices at the storage locations in scope. This is optional and based on country specific requests from the Global Fund CTs. In the Health Products Expiry Review Tool, LFAs can use the ‘Inv Mgmt.’ tab to capture the required information. Based on the locations in scope, additional rows should be added to the ‘Inv Mgmt.’ tab to capture the necessary information. Also, if requested by the Global Fund CT, the value of expired and at risk of expiry products should be calculated using the reference prices provided and aligned with the Global Fund CT (Ex-works price). This data should also be captured in the review tool on the tab ‘10. Value of exp & at-risk prod’.

The recommended frequency of this verification is annual for all High Impact and Core portfolios. However, the frequency depends on the specific needs, risks and context of each portfolio. Based on historical data and results of annual assessments, Global Fund CTs can request to do more frequent assessments to monitor and mitigate risks of expiries.

The final scope should be agreed with the Global Fund CT based on risk, country context, and feasibility. The details of the scope should be clearly captured in the ‘Scope’ tab of the excel tool.

- Tasks

  - Expiry management overview

With the aid of the questionnaire provided in the Health Products Expiry Review Tool,  LFAs should capture key inputs regarding expiry management of commodities under review, including:

- Recording of expiry dates in inventory systems or stock cards.

- Availability of systems or reports that flag products approaching expiry.

- Staff training and application of First-Expiry-First-Out (FEFO) stock management.

- Sharing of routine stock status reports across levels to enable redistribution of near-expiry stock.

- Implementation of redistribution mechanisms for near-expiry stock.

- Availability of SOPs or guidelines for expiry management.

- Processes in place for safe disposal of expired commodities through approved mechanisms.

  - Quantifying expired Products and Risk of Expiry

LFA should conduct site visits and review inventory records, warehouse management systems, and physical stock counts. For each location under the scope of the review, the LFA should collect the following data points for all relevant products:

- Product code

- Product name

- Facility / warehouse name

- Batch number

- Expiry date

- Batch quantity

- Average Monthly Consumption (AMC) or average quantity issued to lower levels

- Source of funding (Global Fund vs. other sources)

In addition, at each location and for each disease program, the LFA should select two product lines from inventory records and conduct a physical verification to confirm:

- Actual batch quantities in stock

- Corresponding batch numbers

- Expiry dates recorded versus physically observed

Any discrepancies between digital records and physical stock should be documented and explained where possible.

  - Analysis and recommendations

The LFA should provide consolidated analysis including:

- Total volumes and estimated value (if requested by the Global Fund CT) of expired and at-risk products. This data should be captured in the review tool in the tab ‘10. Value of exp & at-risk prod’  .

- Main drivers contributing to expiries or expiry risks

- Identified system or operational weaknesses

- Explanation of significant stock imbalances or pipeline issues

Recommendations should be:

- Specific and actionable

- Prioritized and practical

- Time-bound where feasible

- Clearly assigning responsibility for implementation

- Outputs / Deliverables

The LFA should submit the completed Health Products Expiry Review Tool  including root-cause analysis and recommendations.

- Service Delivery

This assignment should be led by the LFA PSM expert, with support from other LFA team members as required. Level of effort and site coverage should be agreed with the Global Fund Country Team before commencing the verification based on scope and risk considerations.

- Fraud or Irregularities

If the review identifies potential fraud or irregular practices, the LFA must follow established Global Fund communication protocols to ensure appropriate escalation.

The tool is available on the Global Fund LFA website under the section ‘ Procurement and Supply Management’